## Cover
INTERSITE CORRIDOR RELOCATE PHASE 1
Complete Stage Deliverables Listing
Planning Document - Stage 2
2013 Master
Rev 0

## G2Plan
Stage 2 Key Inputs | Gate 2 Key Deliverables | SCL Rep | SCL Forecast | SCL Forecast | Due date |  | 2013-10-01 |  |  |  | 2013-11-01 |  |  |  | 2013-12-01 |  |  |  |  | 2014-01-01 |  |  |  | 2014-02-01 |  |  |  | 2014-03-01
|  |  | Start | Finish |  | 2013-09-30 | 2013-10-07 | 2013-10-14 | 2013-10-21 | 2013-10-28 | 2013-11-04 | 2013-11-11 | 2013-11-18 | 2013-11-25 | 2013-12-02 | 2013-12-09 | 2013-12-16 | 2013-12-23 | 2013-12-30 | 2014-01-06 | 2014-01-13 | 2014-01-20 | 2014-01-27 | 2014-02-03 | 2014-02-10 | 2014-02-17 | 2014-02-24 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-24 | 2014-03-31
1. Project Objectives and Strategies | Updated POS | DW |  |  | 2013-11-04 | 2013-11-04: Updated POS
2. External Interfaces | Initial Public Affairs Plan | AA | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-12-16 | 2013-12-16: Initial Public Affairs Plan
| Early Commercial Agreements | AA | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-12-16 | 2013-12-16: Early Commercial Agreements
| Commercial Structure / Responsibilities | AA | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-12-16 | 2013-12-16: Commercial Structure / Responsibilities
3. Economics, Commitments and Funding | Updated Business Case / Economics | SX | 2013-08-01 08:00 | 2013-08-01 16:00
| Early Financial Controls Plan Sign Off | DW | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-12-16 | 2013-12-16: Early Financial Controls Plan Sign Off
| Appropriation Plan | DW | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-12-16 | 2013-12-16: Appropriation Plan
| Gate 2 Review Package for IPR | DW |  |  | 2014-01-20 | 2014-01-20: Gate 2 Review Package for IPR
| Gate 2 Review Package | DW |  |  | 2014-02-17 | 2014-02-17: Gate 2 Review Package
| Provide projected OPEX costs | MP | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-12-02 | 2013-12-02: Provide projected OPEX costs
4. Organization and Staffing | Updated Organization Plan | DW |  |  | 2013-11-04 | 2013-11-04: Updated Organization Plan
| Develop SCL Org Chart | DW |  |  | 2013-11-04 | 2013-11-04: Develop SCL Org Chart
| Obtain AMEC Org Chart | DW |  |  | 2013-11-04 | 2013-11-04: Obtain AMEC Org Chart
| Staffed Team | DW | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-11-04 | 2013-11-04: Staffed Team
| Develop SCL Team List | DW |  |  | 2013-11-04 | 2013-11-04: Develop SCL Team List
| Obtain AMEC Team List | DW |  |  | 2013-11-04 | 2013-11-04: Obtain AMEC Team List
| Stakeholder/ Team Alignment Plan 1st Draft | DW |  |  | 2013-11-04 | 2013-11-04: Stakeholder/ Team Alignment Plan 1st Draft
| Complete Team Alignment Session | DW |  |  | 2013-11-04 | 2013-11-04: Complete Team Alignment Session
| Develop a Stage 2/3 decision Road Map | DW |  |  | 2013-11-04 | 2013-11-04: Develop a Stage 2/3 decision Road Map
| Stakeholder/ Team Alignment Plan - Sign Off | DW |  |  | 2013-12-09 | 2013-12-09: Stakeholder/ Team Alignment Plan - Sign Off
| Early Interface Agreements | TT | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-10-28 | 2013-10-28: Early Interface Agreements
| Develop Interface Agreement Log | TT |  |  | 2013-10-28 | 2013-10-28: Develop Interface Agreement Log
| Develop initial Interface Agreements | TT |  |  | 2013-10-28 | 2013-10-28: Develop initial Interface Agreements
5. Project Planning and Issues | Road Map | DW
| Early Project Plan for Estimating Group | MG | 2013-06-06 08:00 |  | 2013-11-18 | 2013-11-18: Early Project Plan for Estimating Group
| Early Project Plan 1st draft for Review | MG |  |  | 2013-11-18 | 2013-11-18: Early Project Plan 1st draft for Review
| Early Project Plan - Sign Off | MG |  |  | 2013-12-09 | 2013-12-09: Early Project Plan - Sign Off
| Project Issues Identified | DW | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-11-25 | 2013-11-25: Project Issues Identified
| Develop& Maintain Key Issue Action Plan | DW |  |  | 2013-11-25 | 2013-11-25: Develop& Maintain Key Issue Action Plan
| Define Studies to be completed in S3 | AA |  |  | 2013-10-24 | 2013-10-28: Define Studies to be completed in S3
| Update IDROP Log | KT | 2013-08-01 08:00 | 2013-08-01 16:00 | 2014-01-13 | 2014-01-13: Update IDROP Log
| TQA Plan and Assessment | KT | 2014-01-01 | 2014-01-30 |  | 2014-01-13: TQA Plan - Manage to closure
| TQA Plan - Manage to closure | KT |  |  | 2014-01-13
| Early Real Estate Permits (SCL Lease) | TT | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-11-25 | 2013-11-25: Early Real Estate Permits (SCL Lease)
6. Quality | Initial Project Quality Plan 1st draft for Review | SA | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-11-18 | 2013-11-18: Initial Project Quality Plan 1st draft for Review
| Initial Project Quality Plan - Sign Off | SA |  |  | 2013-12-16 | 2013-12-09: Initial Project Quality Plan - Sign Off
| Early ESSS | SA | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-11-18 | 2013-11-18: Early ESSS
7. Selection and Definition | EPDB 1st Draft for Review | KT | 2013-03-06 08:00 | 2013-05-31 16:00 | 2013-11-25 | 2013-11-25: EPDB 1st Draft for Review
| Approved Engineering Plan for Stage 3 (SPI 6) | TT |  |  | 2013-11-18 | 2013-11-18: Approved Engineering Plan for Stage 3 (SPI 6)
| Preliminary Engineering Plan for Stage 4 | TT |  |  | 2013-11-18 | 2013-11-18: Preliminary Engineering Plan for Stage 4
| Early Risk Assessment Plan | KT |  |  | 2013-10-14 | 2013-10-14: Early Risk Assessment Plan
| Early Risk Assessments | KT |  |  | 2013-10-14 | 2013-10-14: Early Risk Assessments
| EPDB - Sign Off | KT | 2013-07-15 | 2013-07-17 | 2014-01-20 | 2014-01-20: EPDB - Sign Off
| Operability and Reliability Considerations | MP
| Develop Service Level Agreement | MP | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-10-21 | 2013-10-21: Develop Service Level Agreement
| Initial GRS | KT | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-10-28 | 2013-10-28: Initial GRS
| Early Constructability reviews | MJC | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-10-14 | 2013-10-14: Early Constructability reviews
| Identify critical lifts and if Lift Studies are Required | TT | 2013-08-01 | 2013-08-01 | 2013-11-04 | 2013-11-04: Identify critical lifts and if Lift Studies are Required
| Value Improving Practices Plan | KT | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-10-21 | 2013-10-21: Value Improving Practices Plan
| Identify Stage 3 VIPs | KT |  |  | 2013-10-21 | 2013-10-21: Identify Stage 3 VIPs
| IER - Review | AA | 2013-06-14 | 2013-06-14 | 2013-10-21 | 2013-10-21: IER - Review
| Early CRTF - Review | AA | 2013-08-09 | 2013-08-12 | 2013-10-21 | 2013-10-21: Early CRTF - Review
| MCOS | KT | 2013-08-01 | 2013-08-01 | 2013-10-21 | 2013-10-21: MCOS
| Facility Capacity Summary | KT | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-10-21 | 2013-10-21: Facility Capacity Summary
| Testing Summary | MP | 2013-08-01 08:00 | 2013-08-01 16:00 | 2013-10-21 | 2013-10-21: Testing Summary
8. Execution | Early Construction Plan 1st Draft | DA | 2013-08-09 | 2013-08-09 | 2013-11-11 | 2013-11-11: Early Construction Plan 1st Draft
| Identify special equipment list | DA |  |  | 2013-11-11 | 2013-11-11: Identify special equipment list
| Develop high-level sequence of construction | DA |  |  | 2013-11-11 | 2013-11-11: Develop high-level sequence of construction
| Develop MC and turnaround strategy | DA |  |  | 2013-11-11 | 2013-11-11: Develop MC and turnaround strategy
| Develop the tie in strategy | DA |  |  | 2013-11-11 | 2013-11-11: Develop the tie in strategy
| Develop Work Authorization Strategy | DA |  |  | 2013-11-11 | 2013-11-11: Develop Work Authorization Strategy
| Develop Modularization Strategy | DA |  |  | 2013-11-11 | 2013-11-11: Develop Modularization Strategy
| Develop Site Transportation Plan | DA |  |  | 2013-11-11 | 2013-11-11: Develop Site Transportation Plan
| Develop Camp and Bus Requirement | DA |  |  | 2013-11-11 | 2013-11-11: Develop Camp and Bus Requirement
| Early Construction Plan for EPP | DA |  |  | 2013-11-18 | 2013-11-18: Early Construction Plan for EPP
| Early Project Operations Plan 1st Draft | MP |  |  | 2013-11-11 | 2013-11-11: Early Project Operations Plan 1st Draft
| Identify OPEX Costs | MP | 2013-08-01 | 2013-08-01 | 2013-11-11 | 2013-11-11: Identify OPEX Costs
| Preliminary Start up & training costs | MP |  |  | 2013-11-11 | 2013-11-11: Preliminary Start up & training costs
| Identify Spares Requirement | MP |  |  | 2013-11-11 | 2013-11-11: Identify Spares Requirement
| Obtain Ruling for spares | MP |  |  | 2013-11-11 | 2013-11-11: Obtain Ruling for spares
| Preliminary Start Up Plan | MP |  |  | 2013-11-11 | 2013-11-11: Preliminary Start Up Plan
| Early Project Operations Plan - Sign Off | MP |  |  | 2013-12-09 | 2013-12-09: Early Project Operations Plan - Sign Off
9. Project Estimates and Control | Gate 2 Cost Estimate | RD |  |  | 2013-01-27 | 2014-01-27: Gate 2 Cost Estimate
| Estimate Basis Memorandum | RD |  |  | 2013-01-27 | 2014-01-27: Estimate Basis Memorandum
| Estimate Confidence Package | RD |  |  | 2013-01-27 | 2014-01-27: Estimate Confidence Package
| Validation | RD | 2015-02-27 | 2015-02-27 | 2013-01-20 | 2014-01-27: Validation
| COSE Stage 3 | All | 2013-07-26 | 2013-07-26 | 2013-12-09 | 2013-12-09: COSE Stage 3
| PRC | RD | 2014-01-23 | 2014-01-23 | 2014-02-17 | 2014-03-03: PRC
| Gate 2 Schedule Estimate | MC |  |  | 2013-12-09 | 2013-12-09: Gate 2 Schedule Estimate
| AMEC Detailed Schedule for Stage 3 | TT |  |  | 2013-12-09 | 2013-12-09: AMEC Detailed Schedule for Stage 3
| Critical Path Schedule (E&P) | MC |  |  | 2013-12-09 | 2013-12-09: Critical Path Schedule (E&P)
| Critical Path Schedule EPC | MC |  |  | 2013-12-09 | 2013-12-09: Critical Path Schedule EPC
| Schedule Risk | MC |  |  | 2013-12-09 | 2013-12-09: Schedule Risk
| Develop SGMS Schedule | MC | 2013-05-13 | 2013-05-13 | 2013-12-09 | 2013-12-09: Develop SGMS Schedule
| Scope Tracking and Management Plan | MC |  |  | 2013-12-09 | 2013-12-09: Scope Tracking and Management Plan
| Early Project Controls Plan for Estimating | MC |  |  | 2013-12-02 | 2013-12-02: Early Project Controls Plan for Estimating
| Preliminary MOC Process and Authorities | MC |  |  | 2013-12-02 | 2013-12-02: Preliminary MOC Process and Authorities
| Early Project Controls Plan - Sign Off | MC | 2013-07-18 | 2013-07-18 | 2013-12-09 | 2013-12-09: Early Project Controls Plan - Sign Off
10. Purchasing and Materials Management | Work Breakdown Structure | MC | 2013-07-26 10:19 | 2013-07-29 10:19 | 2013-10-28 | 2013-10-28: Work Breakdown Structure
| Initial Contracting Strategy | MJC |  |  | 2013-10-21 | 2013-10-21: Initial Contracting Strategy
| Contracting Strategy Engineering | MJC |  |  | 2013-10-21 | 2013-10-21: Contracting Strategy Engineering
| Contracting Strategy Construction Management | MJC |  |  | 2013-10-21 | 2013-10-21: Contracting Strategy Construction Management
| Initial Purchasing Strategy /Plan 1st Draft for Review | MJC |  |  | 2013-11-18 | 2013-11-18: Initial Purchasing Strategy /Plan 1st Draft for Review
| Preliminary Long Lead Equipment List | MJC |  |  | 2013-11-18 | 2013-11-18: Preliminary Long Lead Equipment List
| Long Lead Equipment Duration | MJC |  |  | 2013-11-18 | 2013-11-18: Long Lead Equipment Duration
| Develop List of Potential Bidders | MJC |  |  | 2013-11-18 | 2013-11-18: Develop List of Potential Bidders
| Early Purchasing Projections | MJC |  |  | 2013-11-18 | 2013-11-18: Early Purchasing Projections
| Development of Preliminary List of Special Loads | MJC |  |  | 2013-11-18 | 2013-11-18: Development of Preliminary List of Special Loads
| Initial Purchasing Strategy- Sign Off | MJC |  |  | 2016-12-16 | 2013-12-16: Initial Purchasing Strategy- Sign Off
| Early Material Management Plan 1st draft for Review | MJC |  |  | 2013-11-25 | 2013-11-25: Early Material Management Plan 1st draft for Review
| Identify Receiving and Storage Locations | MJC |  |  | 2013-11-25 | 2013-11-25: Identify Receiving and Storage Locations
| Early Material Management Plan - Sign Off | MJC |  |  | 2013-12-16 | 2013-12-16: Early Material Management Plan - Sign Off
11. SHE and Security | Health RAs/ Preliminary Project Health Plan 1st Draft | MJC |  |  | 2013-11-25 | 2013-11-25: Health RAs/ Preliminary Project Health Plan 1st Draft
| Preliminary Regulatory Compliance Plan 1st Draft | AA |  |  | 2013-11-25 | 2013-11-25: Preliminary Regulatory Compliance Plan 1st Draft
| Preliminary Environmental Management Plan 1st Draft | AA |  |  | 2013-11-25 | 2013-11-25: Preliminary Environmental Management Plan 1st Draft
| Health RAs/ Preliminary Project Health Plan - Sign Off | MJC |  |  | 2013-12-16 | 2013-12-16: Health RAs/ Preliminary Project Health Plan - Sign Off
| Preliminary Regulatory Compliance Plan - Sign Off | AA |  |  | 2013-12-16 | 2013-12-16: Preliminary Regulatory Compliance Plan - Sign Off
| Preliminary Environmental Management Plan - Sign Off | AA |  |  | 2016-12-16 | 2013-12-16: Preliminary Environmental Management Plan - Sign Off
12. Information Management and Reporting | Information Management Plan - 1st Draft | SA |  |  | 2013-11-25 | 2013-11-25: Information Management Plan - 1st Draft
| Information Management Plan - Sign Off | SA |  |  | 2016-12-16 | 2013-12-16: Information Management Plan - Sign Off
13. Project Assessments | Project Review Plan | DW | 2015-01-27 | 2015-01-27 | 2013-12-09 | 2013-12-09: Project Review Plan
| Schedule IPR sessions | AA |  |  | 2013-12-09 | 2013-12-09: Schedule IPR sessions
| IPR Sessions | DW |  |  | 2014-02-03 | 2014-02-03: IPR Sessions
| Gate 2 IPR Report | DW |  |  | 2014-03-03 | 2014-02-17: Gate 2 IPR Report
| TQA Endorsement | DW | 2014-01-17 | 2014-01-17 | 2014-03-17 | 2014-03-17: TQA Endorsement
| G2 Approval | DW |  | 2014-01-31 08:00 | 2014-03-24 | 2014-03-24: G2 Approval
14. Learnings and Improvements | Application of Lessons Learned | SA | 2013-06-03 08:00 | 2013-06-07 16:00 |  | 2013-10-14: Application of Lessons Learned
| Identify applicable LL's | SA |  |  |  | 2013-10-14: Identify applicable LL's
DW Daniela Wilson
MJC Mike Cole
AA Aziz Ahmed
KT Keith Timms
TT Tony Tran
SA Salman Ahmed
AK Allyse Kreiser
MP Mike Papp
MC Malcolm Campbell
RD Rahul Datta
DA Daryl Adams
MG Matt Galachiuk
Note on N32: stimms: Special causes this to be bold

## Table 1 G2 Deliverables
Project: INTERSIRE CORRIDOR RELOCATE PHASE 1
Table 1 Gate 2 Deliverables
Legend: Please see Tab " TeamList" for initials.
Stage 2 Key Inputs | Gate 2 Key Deliverables | Level of Definition | Responsible |  |  | STATUS | Comments
|  |  | SCL | SCL Rep | AMEC
1. Project Objectives and Strategies | · Updated POS | F | R | DW |  | In progress
| · Project Categorization | F | R | CK |  | Complete
2. External Interfaces | · Initial Public Affairs Plan | I | R | AA |  |  | Tracey Welsh
| · Early Commercial Agreements | I | R | AA |  | in progress | with Shell, AMI
| · Commercial Structure / Responsibilities |  | R | AA
3. Economics, Commitments and Funding | · Updated Business Case / Economics | U | R | AK
| · Early Financial Controls Plan | I | R | CW |  |  | Cindy Wellock
| · Appropriation Plan | U | R | MJC
| · Gate 2 Review Package | F | R | DW
| · Provide projected OPEX costs | U | R | MP
4. Organization and Staffing | · Updated Organization Plan | U | R
| · Develop SCL Org Chart |  | R | DW
| · Initial Assessment of Stage 4 Staffing requirements |  | R | MJC
| · Obtain AMEC Org Chart |  |  | DW | R
| · Staffed Team | U | R
| · Develop SCL Team List |  | R | DW
| · Obtain AMEC Team List |  |  | DW | R
| · Stakeholder/ Team Alignment Plan | I | R | DW
| · Develop DDM - AMEC |  | S | TT | R
| · Develop Syncrude RASCI |  | R | DW
| · Complete Team Alignment Session |  | R | DW
| · Develop a Stage 2/3 decision Road Map |  | R | DW
| · State the Planned Timing of Transition |  | R | DW
| · Early Interface Agreements |  | R
| · Develop Interface Agreement Log |  | R | TT
| · Develop initial Interface Agreements |  | R | TT
I
5. Project Planning and Issues | · Road Map | F | R | DW
| · Early Project Plan | I | R | MJC
| · Project Issues Identified | U | R
| · Develop Decision Sign Off Form |  | R | TT |  |  | Decision records
| · Develop& Maintain Key Issue Action Plan |  | R | DW
| · Define Studies to be completed in S3 |  | R | AA
| · Develop & maintain IDROP log |  | R | AA
| · TQA Plan and Assessment | I | R | AA
| · TQA Plan - Manage to closure |  | R | AA
| · Early Real Estate Permits | I | R | TT | S |  | Land reservation
6. Quality | · Initial Project Quality Plan |  | R | DW? |  |  | who is JC?
| · Early ESSS |  | R | TT
7. Selection and Definition | · Early Project Development Basis | F | R | AA
| · Approved Engineering Plan for Stage 3 (SPI 6) |  | R | TT
| · Preliminary Engineering Plan for Stage 4 |  | R | TT
| · Project Specification & Standards | I | R | TT
| · Early Risk Assessment Plan | I | R | AA
| · Early Risk Assessments | I | R | AA? |  |  | discuss
| · Operability and Reliability Considerations | I | R | MP
| · Develop Service Level Agreement |  |  | MP
| · Initial GRS | I | R | TT
| · Early Constructability reviews | I | R | MJC
| · Identify PMT member responsible for Managing Constructability Issues |  | R | MJC
| · Identify critical lifts and if Lift Studies are Required |  | S | MJC | R
| · Value Improving Practices Plan |  | R | AA
| · Identify Stage 3 VIPs |  | R | AA
| · IER | F | R | AA
| · Early CRTF |  | R | AA
| · MCOS | I | R | DW?
| · Facility Capacity Summary |  | R | AA
| · Testing Summary |  | R | MP
8. Execution | · Early Construction Plan | I | R | MJC
| · Identify special equipment list |  | R | MJC
| · Develop high-level sequence of construction events |  | R | MJC
| · Develop mechanical completion and turnaround strategy |  | R | MJC
| · Develop the tie in strategy |  | R | MJC | S
| · Develop Work Authorization Strategy |  | R | MJC
| · Develop Modularization Strategy |  | R | MJC
| · Develop Site Transportation Plan |  | R | MJC
| · Develop Camp and Bus Requirement |  | R | MJC
| · Early Project Operations Plan | I | R | MP
| · Identify OPEX Costs |  | R | MP
| · Preliminary Start up & training costs |  | R | MP
| · Identify Spares Requirement |  | R | MP
| · Obtain Ruling for spares |  | R | MP
| · Preliminary Start Up Plan |  | R | MP
9. Project Estimates and Control | · Gate 2 Cost & Schedule Estimate | F | R | ES |  |  | Emin Shao-Estimating lead
| · Estimate Basis Memorandum |  | R | ES
| · Estimate for alternatives |  | S | ES | R
| · Estimate Confidence Package |  | R | ES
| · COSE Stage 3 |  | S | TT | R
| · Gate 2 Schedule Estimate | F | R | MC |  |  | Malcolm Campbell
| · Detailed Schedule for Stage 3 Engineering |  | E | DW | R
| · Critical Path Schedule (E&P) |  | S | MC | R
| · Critical Path Schedule EPC |  | R | MC
| · Schedule Risk |  | R | MC
| · Develop SGMS Schedule |  | R | MC
| · Scope Tracking and Management Plan | F | R | MC
| · Early Project Controls Plan |  | R | MC
| · Preliminary MOC Process and Authorities |  | R | DW
10. Contracting, Purchasing and Materials Management | · Work Breakdown Structure | I | R | MJC
| · Schedule WBS Workshop |  | R | MJC
| · Schedule EWP Workshop |  | R | MJS
| · Initial Contracting Strategy | I | R | MJC
| · Contracting Strategy Engineering |  | R | DW
| · Contracting Strategy Construction Management |  | R | MJC
| · Initial Purchasing Strategy /Plan | I | R | MJC
| · Preliminary Long Lead Equipment List |  | S | MJC | R
| · Long Lead Equipment Duration |  | S | MJC | R
| · Develop List of Potential Bidders |  | S | MJC | R
| · Early Purchasing Projections |  | S | MJC | R
| · Development of Preliminary List of Special Loads |  | S | MJC | R
| · Early Material Management Plan | I | R | MJC
| · Identify Receiving and Storage Locations |  | R | MJC
11. SHE and Security | · Health RAs/ Preliminary Project Health Plan | I | R | DM |  |  | Who is DM?
| · Preliminary SH&E Plan | I | R | TB |  |  | Who is TB?
| · Preliminary Regulatory Compliance Plan (including Permitting Plan) | I | R | AS |  |  | Anne Simpson
| · Preliminary Environmental Management Plan | I | R | AS
12. Information Management and Reporting | · Information Management Plan | F | R | MM |  |  | Maria. M
13. Project Assessments | · Project Review Plan | F | R | AA
| · Schedule IPR sessions |  | R | AA
| · Gate 2 IPR Report | F | R | DW
14. Learnings and Improvements | · Application of Lessons Learned | F | R | TT
| · Identify applicable LL's |  | R | TT
| · Set up LL's review session |  | R | TT

## Table 2 Tech Deliverables
Table 2 Stage 2 Tech Deliverables |  |  | Project: INTERSIRE CORRIDOR RELOCATE PHASE 1
Legend: Please see Tab " TeamList" for initials.
|  |  |  | Level of Definition | Responsible
Key Area |  | Technical Requirement Area | Deliverable |  | SCL | SCL Rep | Jacobs | Notes and Comments | Rev
Discipline Engineering | 1 | Process | Process Design Basis | I |  | TT | R
|  |  | hydraulic calcs and balances | I |  | TT | R
|  |  | process investigation on existing equipment | I |  | TT | R
|  |  | BFD | F |  | TT | R
|  |  | PFD | I |  | TT | R
Discipline Engineering | 2 | Mechanical | Material selection | I |  | TT | R
|  |  | Existing Equipment Evaluation | I |  | TT | R
|  |  | Critical Equipment Strategy | I | R | MP | S
|  |  | Mechanical Equipment List | U |  | TT | R
|  |  | Develop Long Leads list for all disciplines | U |  | TT | R
Discipline Engineering | 3 | Piping | Tie in List | U |  | TT | R
|  |  | Pipeline list | U |  | TT | R
|  |  | Major Valve | U |  | TT | R
Discipline Engineering | 4 | Electrical | Single line diagrams | I |  | TT | R
|  |  | Area Classification dwg | I |  | TT | R
|  |  | Critical tie in list | U |  | TT | R
|  |  | Equipment List | U |  | TT | R
|  |  | Existing Equipment Evaluation | U |  | TT | R
|  |  | Power requirements | I |  | TT | R
|  |  | Provide electrical load summary and basis | U |  | TT | R
Discipline Engineering | 5 | Instrumentation / DCS | Process Control Philosophy/ Description | I |  | TT | R
|  |  | Communication Requirements | I |  | TT | R
|  |  | Process Automation and Instrument list | I |  | TT | R
|  |  | Major inst list | I |  | TT | R
Discipline Engineering | 6 | Civil / Geotech / Structural | Site plan / Plot plan development | U | R | TT | S
|  |  | Aerial drawing make ups on scope | U |  | TT | R
|  |  | Pump and Sub Siting | U |  | TT | R
|  |  | Site work defn and quantities | I |  | TT | R
|  |  | Bldg list | I |  | TT | R
|  |  | Structural requirements | I |  | TT | R
|  |  | Civil Material Quantities Take offs | I |  | TT | R
|  |  | Sump Design and Siting | U |  | TT | R
|  |  | Surface water management & ditching |  |  | TT | R
|  |  | Corridor design - section diagrams | U |  | TT | R
Other | 1 | Execution | Provide Org Chart | F |  | TT | R
|  | Project Mangagement | Provide Jacobs Approval Plan doc | F |  | TT | R
|  |  | Decision Log | F |  | TT | R
|  |  | Issue Log | F |  | TT | R
|  |  | Planning doc for Stage 3 | F |  | TT | R
|  |  | Progress reporting and std meetings | F |  | TT | R
|  |  | Technical Package for all deliverables | F |  | TT | R
|  |  | Execution and Construction Plan doc | F |  | TT | R
1

## Table 3 EPDB
Project: INTERSITE CORRIDOR RELOCATE PHASE 1
Table 3 EPDB
Legend: Please see Tab " TeamList" for initials.
Section # | Document Section | Sub Section | Responsible |  |  | Section # | Document Section | Sub Section | Responsible
|  |  | SCL | SCL rep | AMEC |  |  |  | SCL | SCL rep | AMEC
1 | Project Overview |  |  |  |  | 4 | Project Basis
1.1 |  | Project Background | R | DW |  | 4.3 |  | Design Considerations
1.2 |  | Project Scope Summary | SCL | AA | R | 4.3.1 |  | Equipment Performance Expectations | R | TT
1.3 |  | Scope Alignment with Future/ Other Projects | R | TT |  | 4.3.1.1 |  | Service Factor, Reliability, and Design Life | R | TT
1.4 |  | Engineering Risk Summary | R | TT |  | 4.3.1.2 |  | Turnaround Considerations | R | MP | S
1.5 |  | Project Execution Considerations that Affect the Design | R | MC |  | 4.3.1.3 |  | Equipment Evaluation | S | TT | R
1.6 |  | Regulatory and Enviroonmental Considerations | R | DW |  | 4.3.1.4 |  | Early Certification Requirements | R | TT
1.7 |  | Preliminary Minimum Conditions of Satisfactions | R | MC |  | 4.3.1.5 |  | Early SCL Quality Program Requirements | R | AA
[6 empty] | 4.3.2 |  | Material Selection | S | TT | R
2 | Design Philosophy and Planning Basis |  |  |  |  | 4.3.3 |  | Critical Tie-Ins and Other Tie-Ins | S | MP | R
2.1 |  | Project Design Basis | S | AA | R | 4.3.4 |  | SH&E Basis and Considerations | R | TT
2.2 |  | Project/Equipment Specifications | S | TT | R | 4.3.5 |  | Hazardous Area Clasification |  | TT | R
2.3 |  | Operating and Control Philosophy | R | MP | S | 4.3.6 |  | Human Factors in Design & Industrial Hygiene |  | TT | R
2.4 |  | Maintenance and Reliability Philosophy | R | MP
[6 empty] | 5 | Plot Plan Basis
3 | Studies and Alternative Selection |  |  |  |  | 5.1 |  | Overall Plot Layout |  | TT | R
3.1 |  | Summary of Major Scope Changes since Gate 1 | R | AA |  | 5.2 |  | Equipment Location |  | TT | R
3.2 |  | Alternative Studies Completed | R | AA |  | 5.3 |  | Spacing Requirements |  | TT | R
3.3 |  | Other Studies Completed | R | AA |  | 5.4 |  | Construction Requirements | S | MC | R
3.4 |  | Optimization Studies Planned | R | AA |  | 5.4 |  | Maintenance Requirements | S | MP | R
4 | Project Basis |  |  |  |  | 6 | Utilities Considerations
4.1 |  | Engineering Work Breakdown | R | TT | S | 6.1 |  | Utilities Conditions |  | TT | R
4.1.1 |  | Engineering Contractor Direct Scope/ Activities | R | TT |  | 6.2 |  | Utility Requirements and Impacts |  | TT | R
4.1.2 |  | Equipment Vendor Scope / Activities | R | TT |  | 6.2.1 |  | Steam |  | TT | R
4.1.3 |  | Speciality Services Scope / Activities | R | TT |  | 6.2.2 |  | Water |  | TT | R
4.1.4 |  | Additional Work by Syncrude Project Staff | R | AA |  | 6.2.3 |  | Fuel/ Natural Gas |  | TT | R
4.2 |  | Project Scope Summaries |  | TT |  | 6.2.4 |  | Electrical |  | TT | R
4.2.1 |  | Process |  | TT | R | 6.2.5 |  | Instrument Air |  | TT | R
4.2.2 |  | Mechanical/ Piping |  | TT | R | 6.2.6 |  | Utility Air |  | TT | R
4.2.3 |  | Civil/ Site Preparation |  | TT | R | 6.2.8 |  | Other |  | TT | R
4.2.4 |  | Geotechnical |  | TT | R | 6.3 |  | Utilities Cost | R | ?
4.2.5 |  | Structural |  | TT | R
4.2.6 |  | Electrical |  | TT | R | 7 | Other Considerations
4.2.7 |  | Instrumentation |  | TT | R | 7.1 |  | Chemicals/ Catalyst | S | TT | R
4.2.8 |  | Analyzers |  | TT | R
4.2.9 |  | Process Automation |  | TT | R | 8 | Appendices
4.2.10 |  | Pipelines |  | TT | R | 8.1 |  | Drawing and Data Sheet List |  |  | R
4.2.11 |  | Infrastructure and Offsites |  | TT | R | 8.2 |  | Technical Deliverables and Studies List |  |  | R
4.2.12 |  | Buildings/ HVAC |  | TT | R | 8.3 |  | Engineering Decision Log |  |  | R
4.2.13 |  | Winterization and Insulation |  | TT | R
4.2.14 |  | Fire Protection including Fireproofing/ Coatings |  | TT | R
4.2.15 |  | AMEC E&I Scope of work |  | AA | R

## Table 4 EPP
PROJECT: INTERSITE CORRIDOR RELOCATE PHASE 1
Table 4 EPP
Legend: Please see Tab " TeamList" for initials.
Section # |  | Responsible
| Document Section | SCL | SCL Rep | AMEC
1 | Project Overview (see EPDB project overview section)
1.1 | Background | R | AA
1.2 | Summary of Project Scope (see EPDB) | R | AA
1.3 | Development & Execution | R | DW
1.4 | Schedule | R | DW
1.5 | Interaction with Other Projects/ Activities | R | TT
2 | Project Objectives and Strategies
2.1 | Project Philosophy and Objectives (see POS) | R | DW
3 | Project Categorization | R | DW
4 | External Interfaces (Caryl Flin)
4.1 | Public Affairs Plan | R | DW
4.2 | Commercial Agreements (Rick Nilson) | R | DW
5 | Issues Management
5.1 | Decision Management (more background info required) | R | DW
5.2 | Execution Risks | R | MJC
5.3 | Construction Contractors Risks | R | DA
5.4 | Special Considerations (more background info required) | R | DW
6 | Engineering Plan | R | TT
7 | Value Immproving Practices (VIPs) Plan | R | AA
8 | Risk Assessment Plan | R | AA
9 | Project Schedule (Malcolm is scheduler)
9.1 | Project Master Schedule | R | MJC
9.2 | Project Base-Line Schedule | R | MJC
9.3 | Critical Path Schedule | R | MJC
9.4 | Resource Constraints and Resource Loading | R | DA
9.5 | Stage 3(Optimize/FEED) Schedule | R | DW
9.6 | Schedule Risk | R | MJC
10 | Work Breakdown Structure (Malcolm is project control lead) | R | DA
11 | Contracting Strategy
11.1 | Contracting Elements of Contracting Strategy and the Implications of the Choice of Strategy | R | MJC
11.2 | Alternative Contracting Approaches | R | MJC
11.3 | Contracting Development Schedule | R | MJC
11.4 | Contracting Strategy for Engineering | R | MJC
11.5 | Contracting Strategy - Construction Management | R | MJC
12 | Procurement Strategy
12.1 | Critical Elements of Procurement Strategy | R | MJC
12.2 | Alternative Procurement Strategy | R | MJC
12.3 | Purchase Order Development Schedule | R | MJC
12.4 | Expediting | R | MJC
12.5 | Material Management Onsite | R | MJC
12.6 | Modularization and Pre-Assembly | R | MJC
12.7 | Transportation Requirements | R | MJC
13 | Project Controls Strategy
13.1 | Project Change Management | R | MC
13.2 | Progress Measurement and Reporting | R | MC
13.3 | Cost Reporting and Variance Analysis Requirements | R | MC
13.4 | Stewardship Reports | R | MC
13.5 | Contractor/ Vendor Reporting Practices, Expectations and Frequencies | R | MC
14 | Project Approval Plan
14.1 | Advance Funding | R | MJC
14.2 | Full Funding | R | MJC
15 | Fabrication & Construction Plan
15.1 | Path of Construction (Construction Sequence) | R | DA
15.2 | Modularization & Pre Assembly Strategy | R | DA
15.3 | Constructability | R | DA
15.4 | Work Authorization Plan (Safe Work Plan) | R | DA
15.5 | Site Labour Strategy | R | DA
15.6 | Temporary Construction Infrastructure | R | DA
15.7 | Workface Planning and System for Managing | R | DA
15.8 | Work Shifts and Schedules | R | DA
15.9 | Site Transportation Plan | R | DA
15.1 | Mobilization and Demobilization Plan | R | DA
15.11 | Housing, Bussing and Accommodation Plans | R | DA
15.12 | Construction Equipment | R | DA
15.13 | Heavy Lifts | R | DA
15.14 | Onsite Fabrication Strategy | R | DA
16 | Financial Control Plan (Cindy Wellock provides the plan) |  | MJC
17 | Organization
17.1 | Roles and Responsibilities | R | DW
17.2 | Development of Aligned Team | R | DW
17.3 | SCL Role in Construction Management | R | DW
17.4 | Development/ Execution Leader Transition Plan | R | DW
17.5 | Stakeholder Reviews and Communication | R | DW
17.6 | Project Team Demobilization | R | MJC
18 | Quality Plan
18.1 | TQA Plan |  | DW
19 | Operations & Reliability Plan
19.1 | Operating Plan | R | MP
19.2 | Commisioning & Start-Up Plan | R | MP
19.3 | Reliability Plan | R | TT
20 | Safety, Health Environment & Security Plan
20.1 | SH&E Plan (Tiffany Blake provides info for the plan) | R | MJC
20.2 | Environment Management Plan (Anne Simpson provides info for the plan) | R | MJC
20.3 | Regulatory Compliance Plan (Anne Simpson provides info for the plan) | R | MJC
20.4 | Security (?) | R | MJC
21 | Data / Documentation Plan
21.1 | Project File Code (Maria McLean provides info for the plan) | R | MM
21.2 | Managing Proprietary Information (Maria McLean provides info for the plan) | R | MM
21.3 | Turnover of Project Files and Documents (Maria McLean provides info for the plan) | R | MM
21.4 | Information Technology Infrastructure (Maria McLean provides info for the plan) | R | MM
22 | Project Review Plan | R | DW
23 | Metrics and Benchmarking | R | MC
24 | Lessons Learned | R | TT
25 | Project Closeout | R | MJC
26 | Glossary | R | MJC
25 | Appendices | R | MJC

## Table 6 List of Reviews
Project: INTERSITE CORRIDOR RELOCATE PHASE 1
Legend: R - Required O- Optional
TABLE 6 - STAGE 2 REVIEW/ WORKSHOP SESSIONS | [5 empty] | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | 2012-09-24 | 2012-10-01 | 2012-10-08 | 2012-10-15 | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-18 | 2012-11-25 | 2012-12-03 | Project Executive Colleen Kearney | EDCH Team Leader Timothy MacPherson | Project Manager Development Wendy Adonyi | Project Manager Execution Mark Tuite | Project Development Engineer Daniela Wilson | Project Engineer Kamran Yousufi | Sr. Business Advisor Merv Sokul | Discipline Engineer Civil Andrei Krymkine | Discipline Engineer Structural Quynh Le | Discipline Engineer Mechanical/ Piping Gord Reed | Discipline Engineer Process Inder Rattan | Discipline Engineer Electrical Germain Mallette | Discipline Engineer I&C Yingnan Fu | Discipline Engineer Geotechnical Philip Alsop | Construction Manager TBA | Project Operations Representative Mike Papp | QA Engineering Don Carlson | QA Procurement TBA | PEL Steve Chan | Scheduler Jared Wyatt/ Laurie Knight | Planner Ken Jonah/ Lyle Prokopowich/ Jack Law | Strategy Advisor Rick Morley | Sr. Planning Adisor Hugh Koyata | Land Administration & Paralegal Jocelyne George | Public Affairs Specialist Tracey Welsh | Natural Gas Representative Dave Turner | Utilities Special Project Engineer Waj Arain | Communication Design Team Lead Norm Gaudet | Froth & Water Pipelines Doug Flint | Aurora POS Ken Foley | Offsites POS (froth & water) Rob Dow | Aurora POS (Natural Gas) Floyd Wilton | Procurement Coordinator TBA | Business Advisor Daniel Macdonnell | Sr. Regulatory Advisor Fred Payne | Regulatory Advisor Anne Simpson | SH&E Planner Tiffany Blake | Regulatory Coordinator Sylvia Skinner/ Rochell Young | Jacobs Project Manager Ron Moynihan | Jacobs Project Engineer Murray Welch
# | Reviews | SCL Rep | Status | Date | Facilitator | 2012-04-02: APRIL; 2012-05-07: MAY; 2012-06-04: JUNE; 2012-07-02: JULY; 2012-08-06: AUGUST; 2012-09-03: SEPTEMBER; 2012-10-01: OCTOBER; 2012-11-05: NOVEMBER | SYNCRUDE CANADA LTD | [37 empty] | JACOBS
JACOBS
1 | Project Kick off - Calgary |  | Complete | 2012-02-01
2 | Application of Lessons Learned | KY | complete | 2012-04-23 | [39 empty] | R | R | R | R |  | R | R | R | R | R | R | R |  | R | [22 empty] | R | R | bar: 2012-04-23
3 | TQA Workshop |  | Complete | 2012-01-16 | Brian Lade
Stage 2 VIPs
4 | IER | WA | complete | 2012-04-04 | Tom Werner | [36 empty] | R |  | R | R | R | R |  |  |  |  | R | R | [8 empty] | R | R | R | [12 empty] | R | bar: 2012-04-02
5 | Early CRTF | WA | scheduled | 2012-06-11 | Tom Werner | bar: 2012-06-11
6 | Early Constructability Review 1/2 | MT | scheduled | 2012-06-14 | TBA | bar: 2012-06-11
7 | Early Constructability Review 2/2 | MT | N/R | 2012-06-28 | TBA | bar: 2012-06-25
8 | Class of Facilities | WA | Complete | 2012-04-23 | Kamran Y. | [36 empty] | O | R | bar: 2012-04-23
9 | Plot Plan Review & Initial Equipment Spacing & Layout Review (B-2) | KY | complete | 2012-05-28 | Kamran Y. | [38 empty] | R | O | R | R |  | R | R | R | R | R | R | R | R | R | [5 empty] | R | bar: 2012-05-28
Stage 2 Risk Assessments
10 | Initial Inherent Safety Health and Environmental Review (ISHER) & PERC | KY | Scheduled | 2012-04-30 | Kamran Y. | [38 empty] | R | O | R | R |  | R | R | R | R | R | R | R |  | R | [20 empty] | R | bar: 2012-04-30
11 | GRS Plan | KY | complete | 2012-05-04 | Rick Parson | bar: 2012-04-30
12 | Operability/ Maintanability Considerations Workshop | KY | Scheduled | 2012-06-21 | [39 empty] | R | R | R | R |  | R | R | R | R | R | R | R |  | R | [12 empty] | R | bar: 2012-06-18
13 | Preliminary Operations Risk Assessment | KY | Scheduled | 2012-06-21 | TBA | [38 empty] | R | R | R | R |  | R | R | R | R | R | R | R |  | R | [12 empty] | R | bar: 2012-06-18
14 | What If Analysis Scope | KY |  | 2012-05-28 | TBA | [37 empty] | R | R | O | R | R |  | R | R | R | R | R | R | R | R | R | [5 empty] | R | bar: 2012-05-28
15 | What If Analysis Execution/ Project Plan | KY | TBS | 2012-09-13 | TBA | [38 empty] | R | O | R | R |  |  |  |  | R | [27 empty] | R | R | bar: 2012-04-16; 2012-09-10
16 | Initial Fire Protection Baseline Risk Analysis (FPBRA) ...SPI-21 | KY | complete | 2012-06-18 | TBA | bar: 2012-06-18
17 | NPQC | KY | complete | 2012-04-27 | Kamran Y. | bar: 2012-04-23
18 | Preliminary Geotechnical Risk Assessment | KY | TBS | 2012-05-31 | TBA | [38 empty] | R | O | R | R |  | R | O | R |  | R |  | R | [24 empty] | R | R | bar: 2012-04-16; 2012-05-28
Start Up/ Commissioning
19 | Testing Strategy Workshop | DW |  | 2012-05-14 | N/A | bar: 2012-05-14
Contracting Strategy
21 | WBS Development Workshop | DW | Complete | 2012-05-04 | N/A | [38 empty] | R | R | R | R | [13 empty] | R | bar: 2012-04-30
22 | EWP Development Workshop | DW | Complete | 2012-04-30 | N/A | [38 empty] | R | R | R | R | bar: 2012-04-30
Early Optimization
23 | Early Optimization Scope Identification Workshop | DW | complete | 2011-05-07 | N/A | [36 empty] | R | bar: 2012-05-07
Estimate & Schedule
24 | Estimate KOM | SC | complete | 2012-05-08 | Steve C. | bar: 2012-05-07
25 | G2 Jacobs Estimate Review | SC | Scheduled | 2012-07-06 | N/A | bar: 2012-07-02
26 | Stage 3 Eng. Schedule Review | WA | in progress | 2012-07-20 | N/A | bar: 2012-07-16
27 | Stage 3 COSE Review | KY | in progress | 2012-07-15 | Kamran Y. | bar: 2012-07-09
28 | G2 Schedule RA | JW |  | 2012-09-17 | Steve C. | bar: 2012-09-17
29 | G2 Cost RA | SC |  | 2012-09-17 | Steve C. | bar: 2012-09-17
30 | G2 Estimate Conditioning | SC |  | 2012-09-03 | N/A | bar: 2012-09-03
31 | G2 Estimate Validation | SC |  | 2012-10-01 | N/A | bar: 2012-10-01
32 | PRC | SC |  | 2012-11-16 | N/A | [37 empty] | R | bar: 2012-11-12
Gate 2 Documentation Review
EPDB Review
33 | Project Team Reviews | DW |  | 2012-07-15 | N/A | bar: 2012-07-09
34 | Functional Reviews | DW |  | 2012-08-30 | N/A | bar: 2012-08-27
| L4 | [41 empty] | R | bar: 2012-08-27
| L3 | [41 empty] | R | bar: 2012-08-27
35 | Stakeholders Reviews | DW |  | 2012-09-03 | N/A | bar: 2012-09-03
EPP Review
36 | Project Team Reviews | MT |  | 2012-09-04 | N/A | [37 empty] | R | bar: 2012-09-03
37 | Functional Reviews | MT |  | 2012-10-02 | N/A | bar: 2012-10-01
Gate 2 Reviews
38 | Gate 2 IPR | DW |  | 2012-10-15 | N/A | [36 empty] | R | R | bar: 2012-10-15
39 | Informal G2 IPR Report Read Out | DW |  | 2012-10-19 | N/A | [36 empty] | R | R | bar: 2012-10-15
40 | Formal G2 IPR Report Readout | DW |  | 2012-10-23 | N/A | [36 empty] | R | R | bar: 2012-10-22
41 | Preliminary Gate 3 Review (L3 PD&E) | DW |  | 2012-11-07 | N/A | [37 empty] | R | bar: 2012-11-05
42 | TQA Plan Owner Review | DW |  | 2012-11-12 | N/A | [37 empty] | R | bar: 2012-11-12
43 | Pre TQA Endorsement meeting with TQA Manager | DW |  | 2012-11-14 | N/A | [37 empty] | R | bar: 2012-11-12
44 | Endorsement Meeting with L2 PD&E | DW |  | 2012-11-26 | N/A | [37 empty] | R | bar: 2012-11-25
[6 empty] | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER

## Table 5 Stage 2 Studies
Project: INTERSITE CORRIDOR RELOCATE PHASE 1
Table 5 Stage 2 Studies
Study # | Discipline | Stage 2 - Key Studies | Description
REV
1 | All | Executive Summary | Overview Technical, Comparative, Screening, Route 1.1 Route 3.1
2 | All | Technical Analysis/ Evaluation of Corridor Relocation | Route 1.1 Route 3.1
3 | All | Comparative Route Options Evaluation | Study 2 Route Options Route 1.1 Route 3.1
4 | Process | Process Design Basis | One composite report common to both options
5 | Process | Froth Pipeline Hydraulic Study | One composite report with sections for each route option
6 | Process | Water Pipeline Hydraulic Study | One composite report with sections for each route option
7 | Process | Natural Gas Pipeline Hydraulic Study | One composite report with sections for each route option
8 | Process/Mechanical | Evaluation of Exisitng Pump Capacity - Optimization | One report as applicable for Route 3.1 Optimization probably not applicable for Route 1.1
9 | Mechanical | Pump / Compressor Modifications / Expansions / Additions | One report as applicable for Route 3.1 Optimization probably not applicable for Route 1.1
10 | Electrical | Design Basis | Conductors, OPGW/OHGW and Insulation Design Basis and Calculations (One composite report common to both options)
11 | Electrical | Design Basis | Cable loading criteria including proposed weather load loading (AUEC, AESO) including transmission line sizing calculations (one composite report common to both route options)
12 | Electrical | Design Basis | Tower selecions, Spacing and calculation of ROW width (One composite report common to both options)
13 | Electrical | Design Basis | Identification of Terms of reference applicable to pipeline inductions (one composite report common to both route options)
14 | All (Civil) | Input to Regulatory Scoping review | Stage 2 prediction for Regilatory Scoping review by SCL/AMEC Route 1.1 Route 3.1
15 | All | Input to Decision Analysis | SWOT - Strengths / Weaknesses / Opportunities / Threats Route 1.1 Route 3.1
16 | All (Pipeline) | Tie in philosophy and Constructability | Led by Pipeline, sections by Civil, electrical, I&C Drawings of tie-in points, cross sections, installation typicals Pipelines, 260 kv transmission line, roads, FO cable Sequencing and logistics Route 1.1 Route 3.1
17 | All (Estimating) | Cost Estimate (raw inputs) and Narrative | Route 1.1 Route 3.1

## Table 6 Early Stage 3 Studies
Project: INTERSITE CORRIDOR RELOCATE PHASE 1
Table 6 Early Stage 3 Studies
Study # | Discipline | Stage 2 - Key Studies | Description
REV
1 | Civil (Geotechnical) | Geotechnical Assessment of corridor route | for foundation design, route optimization, ROW width Route 1.1 Route 3.1
2 | Civil (Survey) | Survey of ROW of corridor route | For route optimization, regulatory applications, final hydraulic Topo Route 1.1 Route 3.1
3 | Electrical | Tower load study / capacity requirements | New tower design, exisitng tower at tie-in points (One composite report common to both options)
4 | Electrical | Design Basis | Electrical clearances, safety requirements, vegetation control (One composite report common to both options)
5 | Electrical | Electrical utility study - corridor reroute | One composite report with sections for each route option
6 | Civil / Pipeline | Input to specific stage 3 regulatory application -SRD | Route 1.1 Route 3.1
7 | Electrical | Input to specific stage 3 regulatory application -AUEC | Route 1.1 Route 3.1
8 | Civil | Input to specific stage 3 regulatory application -Transport Canada | Route 1.1 Route 3.1
9 | Project | Input to specific stage 3 regulatory application -Waters Act | Route 1.1 Route 3.1